## Pointers (hidden)
For trracking the Revenue Realization, Resource Burn Rate and Gross Margins
Revenue Realization | How much of the expected/billed revenue is actually realised | Actual Revenue by Planned Revenue
Resource Burn Rate | To be measured in Cost | Burn Rate = Total Resource Cost/Time Period
Monthly Burn | Resource Cost by Number of Months
for Efficiency | Revenue/Resource Count
Gross Margin | (Revenue-Cost) by Revenue
Net Burn | Cost-Revenue

## Data Sheet (hidden)
Roles | Emp/Contractor | Skill
Google Delivery Lead | Employee | Dev
Integration Lead | Contractor | QA
Google Tech Lead |  | UAT
Project Manager |  | Deployment
Business Analyst
CX Design Lead
CX Designer
Google Developer
QA
BI Dashboard Lead
BI Dashboard UI Developer
ETL Developer
Genesys Developer
UI / UX Developer
Fullstack Developer
QA Lead
Solution Architect
CI Optimization Lead
Data Analyst
Google Support Lead
Google Support
Program Lead
SAFe Coach
RTE
Product Owner

## Resource Allocation (hidden)
Project Name | Employee Code | Employee Name | Emp/Contractor | Skill | Role | Fortnight | Allocated Hrs | Actual Hrs | Cost per Hr | Actual Cost
Auto Case - Auto |  |  | Employee | Dev | Project Manager | F1 | 160 | 180 | 100 | 18000
Auto Case - Auto |  |  |  |  | Integration Lead | F1 | 200 | 220 | 50 | 11000
Auto Case - Auto |  |  |  |  | Business Analyst | F2 | 150 | 200 | 30 | 6000
Auto Case - Pharma D |  |  |  |  | Google Tech Lead | F1 | 110 | 150 | 80 | 12000
Auto Case - Pharma D |  |  |  |  | CX Design Lead | F2 | 80 | 150 | 100 | 15000

## Project Summary (hidden)
Project Name | Start Date | End Date | Total Revenue | Total Cost | Project Burn Rate | Project GM | Burn Status | Cummulative Status (Project Burn + Gross Margim)
Auto Case - Auto | 2025-01-01 | 2026-03-31 | 200000 | 35000 | 0.175 | 0.825 | Green | Amber
Auto Case - Pharma D | 2025-01-15 | 2026-04-15 | 450000 | 27000 | 0.06 | 0.94 | Green | Amber

## Project Wise Revenue (hidden)
Project Code | Project Name | Period (Month) | Planned Revenue | Actual Revenue
HUM0001 | Auto Case - Auto | 2026-01-26 | 500000 | 200000
HUM0002 | Auto Case - Pharma D | 2026-01-26 | 800000 | 450000

## Project Timeline Burn (hidden)
Project Name | Period (Fortnight) | Total Cost | Actual Revenue | Revenue Realised | Burn Rate | Gross Margin | Burn Status
Auto Case - Auto | F1 | 29000 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Auto Case - Auto | F2 | 6000 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Auto Case - Pharma D | F1 | 12000 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Auto Case - Pharma D | F2 | 15000 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Data Fields (hidden)
Client Name | Start Date | End Date | Project Code | Description | Project Revenue | Capability | SOW SF ref | SOW Reveneue | Gross margin

## Sheet7 (hidden)
|  |  | Values |  | Sum of Total Cost
Project Code | Jan-26 | Project Name | Count of Emp ID | Sum of Total Cost | Project Code | Project Name | Employee Name | Jan-26 | Total
HUM0001 | 25% | Auto Case - Auto | 1 | 737.3561 | HUM0001 | Auto Case - Auto | Aanchal Garg | 100% | 6303.4495
| 100% | Auto Case - Auto | 26 | 458979.7623 |  |  | Abhishek Ganguly | 25% | 737.3561
HUM0002 | 100% | Auto Case - Pharma D | 18 | 378413.2852 |  |  | Aishani Bhatnagar | 100% | 6303.4495
Grand Total |  |  | 45 | 838130.4036 |  |  | Ajeesh Balakrishnan | 100% | 69467.7722
[7 empty] | Amar Utkarsh | 100% | 11432.5624
[7 empty] | Amit Jha | 100% | 21704.6958
[7 empty] | Ananya Borah | 100% | 11432.5624
[7 empty] | Anuj Dubey | 100% | 6303.4495
[7 empty] | Deepak Saini | 100% | 11432.5624
[7 empty] | Harshil Andugulapati | 100% | 11432.5624
[7 empty] | Mitali Tripathi | 100% | 21704.6958
[7 empty] | Natalia Militsa | 100% | 69467.7722
[7 empty] | Nihal Shaik | 100% | 11432.5624
[7 empty] | Niketa . | 100% | 21704.6958
[7 empty] | Nirmal Jose P | 100% | 11432.5624
[7 empty] | Nivedita Dixit | 100% | 6303.4495
[7 empty] | Piyush Lahiry | 100% | 11432.5624
[7 empty] | Pradeep Batchu | 100% | 31380.1797
[7 empty] | Pragya Sood | 100% | 11432.5624
[7 empty] | Pranjal Gupta | 100% | 11432.5624
[7 empty] | Prashant Shewale | 100% | 11432.5624
[7 empty] | Puneet Sharma | 100% | 11432.5624
[7 empty] | Rohit Vasant More | 100% | 11432.5624
[7 empty] | Sachidanand Rai | 100% | 21704.6958
[7 empty] | Salabh Ankur | 100% | 21704.6958
[7 empty] | Saurav Jawahar Rajwani | 100% | 6303.4495
[7 empty] | Vipasha . | 100% | 11432.5624
[6 empty] | Auto Case - Auto Total |  |  | 459717.1185
[5 empty] | HUM0002 | Auto Case - Pharma D | Ankush Hora | 100% | 77674.7579
[7 empty] | Anne Rodelene Pelario Tigol | 100% | 32585.552
[7 empty] | Divya Chaudhary | 100% | 21704.6958
[7 empty] | Ishita Koradia | 100% | 6303.4495
[7 empty] | Koushik C S | 100% | 6303.4495
[7 empty] | Krishna . | 100% | 11432.5624
[7 empty] | Madhurima Boral | 100% | 6303.4495
[7 empty] | Manudeep Yalavali | 100% | 21704.6958
[7 empty] | Mayur Shingavi | 100% | 43909.8057
[7 empty] | Rajeev Kumar | 100% | 11432.5624
[7 empty] | Ravi Khurana | 100% | 21704.6958
[7 empty] | Shalini Dey | 100% | 11432.5624
[7 empty] | Soumyashree Dash | 100% | 48744.3266
[7 empty] | Uddeshya Srivastava | 100% | 6303.4495
[7 empty] | Varshini Mahalingam | 100% | 11432.5624
[7 empty] | Vinoth G | 100% | 21704.6958
[7 empty] | Vivek Ramesh Hatwar | 100% | 11432.5624
[7 empty] | Yashkumar Amrutlal Kavaiya | 100% | 6303.4495
[6 empty] | Auto Case - Pharma D Total |  |  | 378413.2852
[5 empty] | Grand Total |  |  |  | 838130.4036

## Project Master
Project Code | Project Name | Start Date | End Date | Total Budget | Currency | Total Revenue
HUM0001 | Auto Case - Auto | 2025-01-01 | 31-03-2026 | 10000000 |  | 13000000
HUM0002 | Auto Case - Pharma D | 2025-01-01 | 31-03-2026 | 7500000 |  | 9500000

## Resource Rate Card
Roles | Emp/Contractor | Skill |  | Sub Band | Location | Role | Role as per Rate Card | Monthly Rate Card | RATE LIST Employee
Google Delivery Lead | Employee | Dev | A2India | A2 | India | QA | QA | 1474.7122 | Band | US | UK | PHP | India
Integration Lead | Contractor | QA | B1India | B1 | India | CX Designer | CX Designer | 3151.7248 | A | 0 | 0 | 2332.939 | 1474.7122
Google Tech Lead |  | UAT | B1US | B1 | US | Google Developer | Google Developer | 15690.0899 | B | 15690.0899 | 13812.9433 | 3998.606 | 3151.7248
Project Manager |  | Deployment | B2India | B2 | India | Data Analyst | Data Analyst | 3151.7248 | C | 24372.1633 | 18759.5089 | 9201.3542 | 5716.2812
Business Analyst |  |  | C1India | C1 | India | BI Dashboard UI Developer | BI Dashboard UI Developer | 5716.2812 | D | 34733.8861 | 31563.5279 | 16292.776 | 10852.3479
CX Design Lead |  |  | C1US | C1 | US | QA | QA | 24372.1633 | E | 38837.379 | 0 | 21954.9028 | 14237.9761
CX Designer |  |  | C2India | C2 | India | Business Analyst | Business Analyst | 5716.2812
Google Developer |  |  | D1India | D1 | India | BI Dashboard Lead | BI Dashboard Lead | 10852.3479
QA |  |  | D1PHP | D1 | PHP | Project Manager | Project Manager | 16292.776 | RATE LIST Contractor
BI Dashboard Lead |  |  | D1US | D1 | US | CX Design Lead | CX Design Lead | 34733.8861 | Band | India
BI Dashboard UI Developer |  |  | D2India | D2 | India | CI Optimization Lead | CI Optimization Lead | 10852.3479 | A | 0
ETL Developer |  |  | D2US | D2 | US | Program Lead | Program Lead | 34733.8861 | B | 0
Genesys Developer |  |  | E1PHP | E1 | PHP | Overall Program Lead | Overall Program Lead | 21954.9028 | C | 0
UI / UX Developer |  |  | E1US | E1 | US | Engagement Lead | Engagement Lead | 38837.379 | D | 0
Fullstack Developer | [8 empty] | E | 0
QA Lead
Solution Architect |  |  |  |  | Location | Band
CI Optimization Lead |  |  |  |  | US | A1
Data Analyst |  |  |  |  | UK | A2
Google Support Lead |  |  |  |  | PHP | B1
Google Support |  |  |  |  | India | B2
Program Lead | [5 empty] | C1
SAFe Coach | [5 empty] | C2
RTE | [5 empty] | D1
Product Owner | [5 empty] | D2
E1
E2

## Monthly Resource (hidden)
Project Code | Project Name | Month | Emp. Code | Emp. Name | Role | Emp/Contractor | Band | Working | Location | Allocation%
HUM0001 | Auto Case - Auto | 2026-01-26 | Abhishek191376 | Abhishek Ganguly | QA | Employee | A2 | A | India | 25
HUM0001 | Auto Case - Auto | 2026-01-26 | Amit127844 | Amit Jha | 0 | Employee | D2 | D | India | 100
HUM0001 | Auto Case - Auto | 2026-01-26 | Ananya193970 | Ananya Borah | CX Designer | Employee | C2 | C | India | 50
HUM0002 | Auto Case - Pharma D | 2026-01-26 | 10125 | Krishna . | CX Designer | Employee | C1 | C | India | 100
HUM0002 | Auto Case - Pharma D | 2026-01-26 | Madhurima217704 | Madhurima Boral | CX Designer | Employee | B1 | B | India | 50
HUM0001 | Auto Case - Auto | 2026-01-26 | Piyush231958 | Piyush Lahiry | Google Tech Lead | Employee | C1 | C | India | 75
HUM0001 | Auto Case - Auto | 2026-01-26 | Pragya262685 | Pragya Sood | QA Lead | Employee | C2 | C | India | 10
HUM0001 | Auto Case - Auto | 2026-01-26 | Vipasha194680 | Vipasha . | Google Tech Lead | Employee | C1 | C | India | 25

## Monthly Resource Allocation
TRIM | Project Code | Project Name | Emp ID | Employee Name | Emp/Contractor | Band | Working | Location | Role | Cost Per Month | 2026-01-26 | 2026-02-26 | 2026-03-26 | 2026-04-26 | 2026-05-26 | 2026-06-26 | 2026-07-26 | 2026-08-26 | 2026-09-26 | 2026-10-26 | 2026-11-26 | 2026-12-26 | Total Cost
QAIndiaA2 | HUM0001 | Auto Case - Auto | Abhishek191376 | Abhishek Ganguly | Employee | A2 | A | India | QA | 1474.7122 | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 737.3561
0IndiaD2 | HUM0001 | Auto Case - Auto | Amit127844 | Amit Jha | Employee | D2 | D | India | 0 | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
CX DesignerIndiaC2 | HUM0001 | Auto Case - Auto | Ananya193970 | Ananya Borah | Employee | C2 | C | India | CX Designer | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
CX DesignerIndiaC1 | HUM0002 | Auto Case - Pharma D | 10125 | Krishna . | Employee | C1 | C | India | CX Designer | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
CX DesignerIndiaB1 | HUM0002 | Auto Case - Pharma D | Madhurima217704 | Madhurima Boral | Employee | B1 | B | India | CX Designer | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Google Tech LeadIndiaC1 | HUM0001 | Auto Case - Auto | Piyush231958 | Piyush Lahiry | Employee | C1 | C | India | Google Tech Lead | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
QA LeadIndiaC2 | HUM0001 | Auto Case - Auto | Pragya262685 | Pragya Sood | Employee | C2 | C | India | QA Lead | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Google Tech LeadIndiaC1 | HUM0001 | Auto Case - Auto | Vipasha194680 | Vipasha . | Employee | C1 | C | India | Google Tech Lead | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Project ManagerPHPD1 | HUM0002 | Auto Case - Pharma D | Anne219593 | Anne Rodelene Pelario Tigol | Employee | D1 | D | PHP | Project Manager | 16292.776 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 32585.552
Google Tech LeadIndiaC2 | HUM0002 | Auto Case - Pharma D | Rajeev235383 | Rajeev Kumar | Employee | C2 | C | India | Google Tech Lead | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Business AnalystIndiaC2 | HUM0001 | Auto Case - Auto | More186546 | Rohit Vasant More | Employee | C2 | C | India | Business Analyst | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Google Delivery LeadIndiaD1 | HUM0001 | Auto Case - Auto | Salabh264271 | Salabh Ankur | Employee | D1 | D | India | Google Delivery Lead | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
Google DeveloperIndiaB2 | HUM0001 | Auto Case - Auto | Saurav240679 | Saurav Jawahar Rajwani | Employee | B2 | B | India | Google Developer | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Google DeveloperIndiaB1 | HUM0002 | Auto Case - Pharma D | Uddeshya220811 | Uddeshya Srivastava | Employee | B1 | B | India | Google Developer | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Google DeveloperIndiaB1 | HUM0002 | Auto Case - Pharma D | Koushik264032 | Koushik C S | Employee | B1 | B | India | Google Developer | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Data AnalystIndiaB1 | HUM0001 | Auto Case - Auto | Aishani262988 | Aishani Bhatnagar | Employee | B1 | B | India | Data Analyst | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Data AnalystIndiaC2 | HUM0001 | Auto Case - Auto | Nirmal257506 | Nirmal Jose P | Employee | C2 | C | India | Data Analyst | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
QAIndiaB2 | HUM0001 | Auto Case - Auto | Nivedita190935 | Nivedita Dixit | Employee | B2 | B | India | QA | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
QAIndiaC1 | HUM0002 | Auto Case - Pharma D | Vivek261441 | Vivek Ramesh Hatwar | Employee | C1 | C | India | QA | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
CI Optimization LeadIndiaD2 | HUM0002 | Auto Case - Pharma D | Vinoth220450 | Vinoth G | Employee | D2 | D | India | CI Optimization Lead | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
QAIndiaB1 | HUM0001 | Auto Case - Auto | Aanchal261215 | Aanchal Garg | Employee | B1 | B | India | QA | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Business AnalystIndiaC1 | HUM0001 | Auto Case - Auto | Amar210603 | Amar Utkarsh | Employee | C1 | C | India | Business Analyst | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
CI Optimization LeadIndiaD1 | HUM0001 | Auto Case - Auto | Niketa269475 | Niketa . | Employee | D1 | D | India | CI Optimization Lead | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
Google SupportIndiaC1 | HUM0002 | Auto Case - Pharma D | Varshini330835 | Varshini Mahalingam | Employee | C1 | C | India | Google Support | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Google SupportIndiaB2 | HUM0002 | Auto Case - Pharma D | Yashkumar331467 | Yashkumar Amrutlal Kavaiya | Employee | B2 | B | India | Google Support | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Data AnalystIndiaB2 | HUM0001 | Auto Case - Auto | Anuj332005 | Anuj Dubey | Employee | B2 | B | India | Data Analyst | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Google Support LeadIndiaC1 | HUM0001 | Auto Case - Auto | Prashant272119 | Prashant Shewale | Employee | C1 | C | India | Google Support Lead | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Solution ArchitectIndiaD2 | HUM0001 | Auto Case - Auto | Sachidanand156765 | Sachidanand Rai | Employee | D2 | D | India | Solution Architect | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
Solution ArchitectIndiaD2 | HUM0002 | Auto Case - Pharma D | Manudeep251771 | Manudeep Yalavali | Employee | D2 | D | India | Solution Architect | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
QAUSC1 | HUM0002 | Auto Case - Pharma D | Soumyashree332048 | Soumyashree Dash | Employee | C1 | C | US | QA | 24372.1633 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48744.3266
Integration LeadIndiaC2 | HUM0001 | Auto Case - Auto | Puneet262683 | Puneet Sharma | Employee | C2 | C | India | Integration Lead | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Genesys DeveloperIndiaC1 | HUM0001 | Auto Case - Auto | Deepak214130 | Deepak Saini | Employee | C1 | C | India | Genesys Developer | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Program LeadUSD2 | HUM0001 | Auto Case - Auto | Ajeesh87344 | Ajeesh Balakrishnan | Employee | D2 | D | US | Program Lead | 34733.8861 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 69467.7722
Google DeveloperIndiaC1 | HUM0002 | Auto Case - Pharma D | Shalini334240 | Shalini Dey | Employee | C1 | C | India | Google Developer | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Google DeveloperIndiaB1 | HUM0002 | Auto Case - Pharma D | Ishita273057 | Ishita Koradia | Employee | B1 | B | India | Google Developer | 3151.7248 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6303.4495
Google DeveloperUSB1 | HUM0001 | Auto Case - Auto | kt_pradeepb | Pradeep Batchu | Employee | B1 | B | US | Google Developer | 15690.0899 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31380.1797
Project ManagerIndiaD1 | HUM0001 | Auto Case - Auto | 19030 | Mitali Tripathi | Employee | D1 | D | India | Project Manager | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
Project ManagerIndiaC1 | HUM0001 | Auto Case - Auto | 19031 | Harshil Andugulapati | Employee | C1 | C | India | Project Manager | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
Google Delivery LeadIndiaD1 | HUM0002 | Auto Case - Pharma D | 19032 | Ravi Khurana | Employee | D1 | D | India | Google Delivery Lead | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
BI Dashboard LeadIndiaD1 | HUM0002 | Auto Case - Pharma D | 19033 | Divya Chaudhary | Employee | D1 | D | India | BI Dashboard Lead | 10852.3479 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21704.6958
ETL DeveloperIndiaC1 | HUM0001 | Auto Case - Auto | re_nihals | Nihal Shaik | Employee | C1 | C | India | ETL Developer | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
BI Dashboard UI DeveloperIndiaC1 | HUM0001 | Auto Case - Auto | re_pranjalg | Pranjal Gupta | Employee | C1 | C | India | BI Dashboard UI Developer | 5716.2812 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11432.5624
CX Design LeadUSD1 | HUM0001 | Auto Case - Auto | Natalia203158 | Natalia Militsa | Employee | D1 | D | US | CX Design Lead | 34733.8861 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 69467.7722
Overall Program LeadPHPE1 | HUM0002 | Auto Case - Pharma D | Mayur16520 | Mayur Shingavi | Employee | E1 | E | PHP | Overall Program Lead | 21954.9028 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 43909.8057
Engagement LeadUSE1 | HUM0002 | Auto Case - Pharma D | Ankush134427 | Ankush Hora | Employee | E1 | E | US | Engagement Lead | 38837.379 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77674.7579

## Project Burn Summary
Project Code | Project Name | Month | Monthly Cost | Cumulative Project Cost | Remaining Budget | RAG Status | Revenue Till Date | Gross Margin | Gross Margin%
HUM0001 | Auto Case - Auto | 2026-01-26 | 459717.1185 | 459717.1185 | 9540282.8815 | Green | 597632.254 | 137915.1355 | 0.23077
HUM0002 | Auto Case - Pharma D | 2026-01-26 | 378413.2852 | 378413.2852 | 7121586.7148 | Green | 479323.4945 | 100910.2094 | 0.21053

## MoM Resource Utilisation
Project Code | Project Name | Emp Code | Emp Name | Role | Month | Allocation% | Utilisation Status
HUM0001 | Auto Case - Auto | Abhishek191376 | Abhishek Ganguly
HUM0001 | Auto Case - Auto | Amit127844 | Amit Jha
HUM0001 | Auto Case - Auto | Ananya193970 | Ananya Borah
HUM0002 | Auto Case - Pharma D | 10125 | Krishna .
HUM0002 | Auto Case - Pharma D | Madhurima217704 | Madhurima Boral
HUM0001 | Auto Case - Auto | Piyush231958 | Piyush Lahiry
HUM0001 | Auto Case - Auto | Pragya262685 | Pragya Sood
HUM0001 | Auto Case - Auto | Vipasha194680 | Vipasha .
HUM0002 | Auto Case - Pharma D | Anne219593 | Anne Rodelene Pelario Tigol
HUM0002 | Auto Case - Pharma D | Rajeev235383 | Rajeev Kumar
HUM0001 | Auto Case - Auto | More186546 | Rohit Vasant More
HUM0001 | Auto Case - Auto | Salabh264271 | Salabh Ankur
HUM0001 | Auto Case - Auto | Saurav240679 | Saurav Jawahar Rajwani
HUM0002 | Auto Case - Pharma D | Uddeshya220811 | Uddeshya Srivastava
HUM0002 | Auto Case - Pharma D | Koushik264032 | Koushik C S
HUM0001 | Auto Case - Auto | Aishani262988 | Aishani Bhatnagar
HUM0001 | Auto Case - Auto | Nirmal257506 | Nirmal Jose P
HUM0001 | Auto Case - Auto | Nivedita190935 | Nivedita Dixit
HUM0002 | Auto Case - Pharma D | Vivek261441 | Vivek Ramesh Hatwar
HUM0002 | Auto Case - Pharma D | Vinoth220450 | Vinoth G
HUM0001 | Auto Case - Auto | Aanchal261215 | Aanchal Garg
HUM0001 | Auto Case - Auto | Amar210603 | Amar Utkarsh
HUM0001 | Auto Case - Auto | Niketa269475 | Niketa .
HUM0002 | Auto Case - Pharma D | Varshini330835 | Varshini Mahalingam
HUM0002 | Auto Case - Pharma D | Yashkumar331467 | Yashkumar Amrutlal Kavaiya
HUM0001 | Auto Case - Auto | Anuj332005 | Anuj Dubey
HUM0001 | Auto Case - Auto | Prashant272119 | Prashant Shewale
HUM0001 | Auto Case - Auto | Sachidanand156765 | Sachidanand Rai
HUM0002 | Auto Case - Pharma D | Manudeep251771 | Manudeep Yalavali
HUM0002 | Auto Case - Pharma D | Soumyashree332048 | Soumyashree Dash
HUM0001 | Auto Case - Auto | Puneet262683 | Puneet Sharma
HUM0001 | Auto Case - Auto | Deepak214130 | Deepak Saini
HUM0001 | Auto Case - Auto | Ajeesh87344 | Ajeesh Balakrishnan
HUM0002 | Auto Case - Pharma D | Shalini334240 | Shalini Dey
HUM0002 | Auto Case - Pharma D | Ishita273057 | Ishita Koradia
HUM0001 | Auto Case - Auto | kt_pradeepb | Pradeep Batchu
HUM0001 | Auto Case - Auto | 19030 | Mitali Tripathi
HUM0001 | Auto Case - Auto | 19031 | Harshil Andugulapati
HUM0002 | Auto Case - Pharma D | 19032 | Ravi Khurana
HUM0002 | Auto Case - Pharma D | 19033 | Divya Chaudhary
HUM0001 | Auto Case - Auto | re_nihals | Nihal Shaik
HUM0001 | Auto Case - Auto | re_pranjalg | Pranjal Gupta
HUM0001 | Auto Case - Auto | Natalia203158 | Natalia Militsa
HUM0002 | Auto Case - Pharma D | Mayur16520 | Mayur Shingavi
HUM0002 | Auto Case - Pharma D | Ankush134427 | Ankush Hora

## Resource Allocation Till Date
Project Code | Project Name | Emp Code | Emp Name | Role | Total Allocation% | Months Count | Avg Utilisation% | Utilisation Status

## Project Timeline Burn (2) (hidden)
Project Name | Project Name | Period (Monthly) | Total Cost | Actual Revenue | Revenue Realised | Burn Rate | Gross Margin | Burn Status
HUM0001 | Auto Case - Auto | 2026-01-26 | 459717.1185 | 200000 | 100% | 2.2986 | -1.2986 | Red
HUM0002 | Auto Case - Pharma D | 2026-02-26 | 378413.2852 | 450000 | 100% | 0.84092 | 0.15908 | Amber

## Project Wise Summary (hidden)
Project ID | Project Name | Start Date | End Date | Total Budget | Total Effort | Cost till Date | Project Budget | Budget Burn Down
| Auto Case - Auto |  |  |  | 32 | 0 |  | #DIV/0!
Auto Case - Pharma D
Auto Case - PTS
Auto Case - STP
Call Transcription - Auto, PTS, STP
Call Transcription - Pharma D
CCaaS Modernization
Chat Summarization-ProviderSolutions
Chat VA - Pharma D
EAAA - Provider Solutions
EAAA Enhancements - Provider Solutions
Email AAA - MSD
Email AAA - Pharma D
IDP
IDP-EmailAttachments-Pharma
IDP-EmailAttachments-ProviderSolutions
Insights-EAAA-ProviderSolutions
Insightshub
Insights-IDP-ProviderSolutions
IVR Modernization - Auto
IVR Modernization - MSD
IVR Modernization - Pharma D
IVR Modernization - PTS
IVR Modernization - STP
Live Chat - Pharma D
MIAW Upgrade - Connect Portal
MIAW Upgrade - Customer Central Portal
VA Migration
VirtualAssistant - Connect Portal
VirtualAssistant - Customer Centre Portal

## Project Resource Details (hidden)
WEEKLY LOGGED HOURS
Project ID | Project Name | Resource ID | Resource Name | Resource Type | Resource Status | Weekly Rate | Yearly Rate | Wk01 | Wk02 | Wk03 | Wk04 | Wk05 | Wk06 | Wk07 | Wk08 | Wk09 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32 | Wk33 | Wk34 | Wk35 | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52 | Wk53 | Wk54 | Wk55 | Wk56 | Total hrs logged till date | Cost till date | Budget | Budget Burn Down
| Auto Case - Auto |  |  |  | FTE/Contractor |  | 0 | WEEKLY LOGGED HOURS Wk01: 8; WEEKLY LOGGED HOURS Wk02: 8; WEEKLY LOGGED HOURS Wk03: 8; WEEKLY LOGGED HOURS Wk04: 8 | 32 | 0 |  | #DIV/0!
Week on week hours have to be plotted against each resource to achieve the total cost
Need to understand the Factors affecting the change in the weekly rate card of the resources if any
Factors affecting the change in the weekly rate of the resources if any
Is total hrs logged by the resources available on weekly basis
Budget of the resources is available at the start of the project and remains the same throughout?
Start date and end date of the project has to be captured to get the months left
Total Effort is the Resource logged hrs in the project resource details
Total Cost is the yearly rate by hrs logged by the resource
Budget is the rate of the project that comes from the SOW

## Project Resource Details (2) (hidden)
Wk01
Project ID | Project Name | Resource ID | Resource Name | Resource Type | Resource Status | Weekly Rate | Total Hrs Logged | Total Cost | Budget | Budget Burn Down
[5 empty] | FTE/Contractor |  |  | 0 | 1 | 0

## Resource Wise Summary (hidden)
Project ID | Project Name | Resource ID | Resource Name | Resource Type | Cost Per Hr. | Total Hrs | Total Cost | Budget | Budget Burn Down | Week
[7 empty] | 0 | 1 | 0 | Wk01
Wk02